## Sheet1
Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
Collected Aadhaar and other KYC document images and prepared datasets for OCR, CNN, and ML models. Performed image preprocessing, normalization, QR extraction readiness, and metadata preparation for downstream validation. | 1 | everyone | as the data is confidential so not readily available | so we used synthesized data and generated some fake data using libraries | 2025-12-10 | closed | hence we faced trouble in model training as data was limited
Implemented PaddleOCR to extract structured text fields from Aadhaar documents and generated standardized JSON outputs. Built OCR post-processing logic to clean text, validate formats, and prepare extracted data for rule-based and ML validation. | 2 | shravani | proper extraction was not happening | used many ocr extraction techinque at last final selected paddle ocr as it gave better outcome as compared to others | 2025-12-15 | closed
Extracted Aadhaar QR code data and compared it against OCR-extracted fields using rule-based validation. Generated consistency scores and flags to detect mismatches between QR data, OCR text, and document structure. | 3 | pakhee,aishwarya | from addhar proper qr was not detected and decoded | so we decided to upload separate qr image then it was well decoded | 2025-12-17 | closed
Developed a CNN model to classify documents as real Aadhaar, fake Aadhaar, or non-Aadhaar images. Integrated image forensics features to detect tampering indicators such as overlays, font inconsistencies, and artifacts. | 4 | piyush | for fear of overfiting and some time give a worng prediction | so I usedEfficientNetB0 model for transfer learning | 2025-12-15 | closed
Performed face extraction from Aadhaar photo and live/person image for comparison. Applied face-matching logic to verify identity consistency when the document is classified as a real Aadhaar. | 5 | shravani | facing issue to work with deepface like big model as already the project is heavy so it was taking more computation time | so we decided to use light weight models | 2025-12-25
Designed an ML model that takes OCR data, QR validation results, and image forensics inputs. The model produces a final Real/Fake classification with confidence-based fraud risk assessment. | 6 | ashish | Facing an issue while choosing the feature for model training, which is extracted from the OCR output. It's actually a complex issue that can directly make an impact on predictions and can result in false classifications | To select the most important feature, I asked ChatGPT about which feature helps the model perform well on the dataset | 2025-12-17
Integrated OCR, CNN, QR validation, face matching, and ML models into a single end-to-end pipeline. Ensured smooth data flow between modules and real-time decision output in JSON format. | 7 | piyush | sometime all pipeline did not worked according to expectation | So I modify my pipelines | 2026-01-01 | closed
Tested the complete pipeline with multiple Aadhaar scenarios including genuine, tampered, and fake samples. Validated system accuracy, reduced false positives, and ensured readiness for cloud-based deployment. and UI part made | 8 | aishwarya,vaishnavi | Initally the website was not easy too understand | So added step by step procedure to complete the verification | 2026-01-03 | closed